## Sheet1
Project Name | Task Name | Assigned to | Start Date | Days Required | End Date | Progress
Marketing | Market Research | Alice | 45292 | 13 | 45305 | 0.78
Marketing | Content Creation | Bob | 45305 | 14 | 45319 | 1
Marketing | Social Media Planning | Charlie | 45319 | 22 | 45341 | 0.45
Marketing | Campaign Analysis | Daisy | 45340 | 25 | 45365 | 0
Product Dev | Prototype Development | Ethan | 45293 | 18 | 45311 | 1
Product Dev | Quality Assurance | Fiona | 45311 | 10 | 45321 | 0.78
Product Dev | User Interface Design | Gabriel | 45326 | 25 | 45351 | 0
Customer Svc | Service Improvement | Hannah | 45323 | 22 | 45345 | 1
Customer Svc | Ticket Resolution | Ian | 45346 | 25 | 45371 | 1
Customer Svc | Customer Feedback | Julia | 45372 | 30 | 45402 | 0
Financial | Budget Analysis | Kevin | 45324 | 22 | 45346 | 0.1
Financial | Financial Reporting | Mark | 45335 | 21 | 45331 | 0.78
Financial | Investment Planning | Mark | 45370 | 25 | 45395 | 1
Research | Market Trends Analysis | Nathan | 45293 | 23 | 45316 | 0.5
Research | Data Collection | Olivia | 45317 | 32 | 45349 | 0
Research | Research Paper Writing | Peter | 45350 | 27 | 45377 | 0
Development | Software Development | Quinn | 45293 | 36 | 45329 | 1
Development | Feature Enhancement | Rachel | 45330 | 34 | 45364 | 0
Development | Code Review | Sam | 45365 | 30 | 45395 | 0
Production | Manufacturing | Tim | 45294 | 47 | 45341 | 0.3
Production | Quality Control | Ursula | 45339 | 27 | 45366 | 0
Production | Packaging Design | Victor | 45365 | 22 | 45387 | 0
Sales | Lead Generation | Wendy | 45294 | 60 | 45354 | 0.7
Sales | Client Meetings | Xavier | 45297 | 20 | 45317 | 0.78
Sales | Contract Negotiation | Yvette | 45325 | 35 | 45360 | 0
Support | Technical Support | Zoe | 45292 | 25 | 45317 | 1
Support | Bug Fixes | Aaron | 45318 | 31 | 45349 | 1
Support | Software Updates | Bella | 45353 | 22 | 45375 | 0
Operations | Process Optimization | Calvin | 45294 | 30 | 45324 | 0.4
Operations | Inventory Management | Diane | 45325 | 25 | 45350 | 0
Operations | Facility Maintenance | Edward | 45351 | 20 | 45371 | 0
Consulting | Strategic Planning | Fiona | 45293 | 35 | 45328 | 0.6
Consulting | Market Expansion | Gary | 45324 | 32 | 45356 | 0
Consulting | Client Advisory | Helen | 45357 | 25 | 45382 | 0
Training | Employee Training | Isaac | 45295 | 27 | 45322 | 0.8
Training | Certification Programs | Jane | 45319 | 30 | 45349 | 0
Training | Skill Development | Kyle | 45350 | 22 | 45372 | 0
Events | Event Planning | Laura | 45294 | 25 | 45319 | 0.3
Events | Conference Management | Mike | 45325 | 20 | 45345 | 0
Events | Sponsorship Coordinatio | n Nancy | 45346 | 35 | 45381 | 0
Logistics | Supply Chain Management | Oscar | 45294 | 25 | 45319 | 0.5
Logistics | Transportation Planning | Patricia | 45320 | 30 | 45350 | 1
Logistics | Inventory Optimization | Quentin | 45380 | 20 | 45400 | 0
Engineering | Product Design | Rachel | 45293 | 25 | 45318 | 0.2
Engineering | System Integration | Sam | 45324 | 22 | 45346 | 0
Engineering | Prototype Testing | Tom | 45345 | 27 | 45372 | 0